## Project Tracking
Project Tracking Template
Karyna Projects | [6 empty] | Cost/Hours
Priority | Deadline | Project/Task | By | Action | By | % Done | Fixed Cost | Hrs to date
| 2017-03-30 | KR Upgrade site to mobile & format |  |  |  | 80% | Free
High | 2017-03-14 | Select portrait images for vertical homepage slider | K | Amend functions.php; Create new vertical page; New css | S
High | 2017-03-14 | Approve test site warning page format and background | K | Plugin change colors; New css for background; Check display frequency | S
High | 2017-03-14 | Approve test site gallery/video page functionality/format | K | Switch Envira auth code; Create new main, private, menage, video galleries; Create albums; New css; Insert new shortcode into pages. | S
High | 2017-03-14 | Approve test site font changes to Lobster font | K | Disable Cufon fonts; enable and program Google font sizes | S
Mid | 2017-03-20 | Approve test site text box sizing changes (see Contact) | K | Amend css | S
Mid | 2017-03-22 | Review entire site and approve for transfer | K | Finalise all changes | S
Mid | 2017-04-15 | Enable js, css, and html compression/cache and test | S | Test at https://testmysite.thinkwithgoogle.com/
Low | 2017-04-30 | Window close button overlay on Vimeo video play | S | Awaiting response from Envira; not critical as un-fullscreen reverts
Low | 2017-04-30 | Enable shared SSL so site will be https for Google | S | Only site where this works is Siteground so site would have to migrate | S
Low | 2017-04-30 | Resubmit mobile and base https to Google search | S
Low | 2017-04-30 | Establish schedule of backups | S | Send to what email?? | K
Low | 2017-04-30 | Check hacking protection | S
Low |  | Research new themes | K | Critique Halo theme when ported to Wordpress | S
|  | InchByInchHealing |  |  |  | 65% | $400 paid | 40
High |  | Header slider images in same ratio; min width 1366px | K | Insert and test | S
High |  | Page header images in same ratio as slider images | K | Insert and test | S
High |  | Photos of Kimi for Home and About pages | K | Kimi to provide
High |  | Logo | K | Insert and test | S
High |  | Quotes for all pages footers and slider images | K | Kimi to provide
High |  | Social links (LinkedIn; FB; Instagram) | K | Kimi to provide
High |  | Approve Instagram page format | K
Mid |  | Blog post | K | Kimi to provide
Mid |  | Media page? | K | Kimi to provide?
Mid |  | Contact form to forward to what address | K | Kimi to provide. Insert and test | S
Mid |  | Patient questionnaire form content | K | Kimi to provide. Insert and test | S
Mid |  | Update CMS with areas Kimi needs to access | S
Low |  | Enable js, css, and html compression/cache and test | S | Test at https://testmysite.thinkwithgoogle.com/
Low |  | Submit mobile and base http or https to Google search | K
Low |  | Establish schedule of backups | S | Send to what email??
Low |  | Check hacking protection | S
|  | Program & Business Value Management |  |  |  | 90% | $300 paid | 40
High |  | Review format, colours, fonts | K | Note that internal links do not work as will change when ported
High |  | Review content | K
High |  | Contact address, tel, fax, email, social links | K | Insert and test | S
Mid |  | Contact form to forward to what address | K | Insert and test | S
Mid |  | Establish new hosting | K
Mid |  | Port site to new host | S
Low |  | Enable js, css, and html compression/cache and test | S | Test at https://testmysite.thinkwithgoogle.com/
Low |  | Submit mobile and base http or https to Google search | K
Low |  | Establish schedule of backups | S | Send to what email??
Low |  | Check hacking protection | S
|  | Jasmin Singh Law |  |  |  | 65% | $300 unpaid | 15
High |  | Review format, colours, fonts | K | Fonts:http://fontpair.co/; Colour:http://paletton.com
High |  | Review basic pages required | K | Jasmin to provide
Mid |  | Page content | K | Jasmin to provide
Low |  | Enable js, css, and html compression/cache and test | S | Test at https://testmysite.thinkwithgoogle.com/
Low |  | Submit mobile and base http or https to Google search | K
Low |  | Establish schedule of backups | S | Send to what email??
Low |  | Check hacking protection | S
|  | Bridgewater Farmhouse |  |  |  | 90% | $300 paid | 30
High |  | Check photos and specify which in each section | K
High |  | Hotlink to HomeAway reviews | K | Ben to provide
High |  | Logo | K | Insert and test | S
Mid |  | Right sidebar or sep page for availability? | K | Ben to advise; then format as appropriate
Mid |  | Instagram – will there be more entries? | K | Ben to provide
Mid |  | Local area content confirm or expand | K | Ben to provide; then format as appropriate | S
Low |  | Enable js, css, and html compression/cache and test | S | Test at https://testmysite.thinkwithgoogle.com/
Low |  | Submit mobile and base http or https to Google search | K
Low |  | Establish schedule of backups | S | Send to what email??
Low |  | Check hacking protection | S
|  | Red Rock port to Woocommerce |  |  |  | 0% | $500 est | 0
Low |  | Decide whether to commission this work | K | The cost estimate is based on using existing KC Woocommerce format
Low |  | Establish new host | S
Low |  | Install WP and Woocommerce | S | Copy from Karynas Closet
Low |  | Set up style and colors and fonts | S
Karynas Closet
Low |  | Decide whether to do anything with this site | K |  |  | 50% | 0 | 30
Jessa Jones
|  | Mobile site moderately broken and rates badly on test |  | Test at https://testmysite.thinkwithgoogle.com/
The best responsive theme I've found is Soho(BenNorman & Bridgewater)
All sites to SSL
|  | Google is giving listing preference to https sites; In the future all non https pages will be marked with a warning. |  | Bluehost has a low quota on free SSL; Servage seems very technical to implement (and their site is notoriously hackable); Only Siteground upgraded all my sites seemlessly.
|  | Suggest you cleanup redundant and migrate all remaining Servage accounts (of which you have many) and any critical Bluehost accounts. |  | Search for fresh host or open diff Siteground service on their Amsterdam server as distinct from the Chicago one you use now.
Simon Projects | [6 empty] | Cost/Hours
Priority | Deadline | Project/Task | By | Action | By | % Done | Fixed Cost | Hrs to date
|  | gfe2go.com |  |  |  | 50%
|  | Design site allowing self-submission |  | Best site is scarlettblue.com.au
|  | Decide pricing structure |  | Freemium with charges for addons such as 'available now', video,blog. Benefits for cross promotion, banners.
Decide cities for launch
Legality
How to approach potential listers
Languages
|  | personal.gfe2go.com |  |  |  | 0%
|  | Develop Mobile-First based matrix of pages |  | Critique Halo theme when ported to Wordpress
|  | Decide pricing structure |  | Based on flagfall plus extra pages mixed and matched. Other features extra such as hosting, domain, CMS, promotion.
How to approach potential listers
|  | LaCortigiana.com |  |  |  | 60%
Look and feel of current site
Incorporate calendar touring function
What advertising media; what USPs
Approach possible listers
Cities
Languages
|  | MobiTechGuru.com |  |  |  | 0%
Design site allowing self-submission
|  | Wordpress plugins |  |  |  | 0%
|  | Image manipulation for mobiles |  | Check and present based on orientation of image and device; Extras charged to selectively display, display in order, crop each differently, featured image in two formats, resizing on the fly.
|  | Add options to Wordpress Appearance>Customize |  | Show framed version of full screen (not shrunken as at present; Extras charged for other views such as portrait in tablet and mobile, better integration of font and colour, hints (self fill) on css, style identification for css on rollover.
|  | Child theme and plugin base file amendments list |  | Track changes to base files in themes and plugins. Simple comparison of changes on install of new versions.
|  | Redirect to diff page depending on orientation |  | Diff pages or content depending on device orientation